## Slide 1: Technology In Construction
Kranti Kiran Reddy
MD, Janapriya Engineers Syndicate
Convener Credai – Cost & Project Management

## Slide 2: Modular Form Work – Walls & Slabs

## Slide 3: Case study 100 Flats – Stilt + 5 Floors (1000 sft flats)
Excavation and Works up to Plinth – 90 days
Stilt – 30 days
Super Structure – 120 days
BW & Finishes – 180 days
Total Project Time – 420 days
Building Schedule

## Slide 4: Case study 100 Flats – Stilt + 5 Floors (1000 sft flats)
Day 1: Shuttering
Day 2: Shuttering
Day 3: Reinforcement
Day 4: Conduiting & Pouring
Day 5: Deshuttering & Re-shuttering (Prop in place)
Form Work Schedule – One Set

## Slide 5: Case study 100 Flats – Stilt + 5 Floors (1000 sft flats)
Deployment
Consider 25 working days in a month
No of flats per month for 1 set – 5 Flats
To finish in 120 days. Sets to be deployed – 5 sets

## Slide 6: Form Work Costing
Total Floor plate – 20,000 sft
Plinth Area - 16,650 sft (considering 20% CA)
FW area for 5 sets of Flats area – 4160 sft
FW area for Corridor area 50% deployment – 1675 sft
Total FW Area required – 5835 sft (542 Sqm)
Cost of FW @Rs 17000 per sqm – Rs 92.15 Lakhs
Slab Qty Needed:
No of repetitions – 20 repetitions
Cost of Frame approx. – Rs 16000 per sqm
Useful life of frame – 300 repetitions. (Rs 53.33 per sqm)
Cost of Ply approx. – Rs 1000 per sqm (Rs 16.66 per Sqm)
Useful life for Ply – 60 repetitions
Effective cost – Rs 70 per sqm
Effective Cost on Project – Rs 6.5 lakhs
No of Similar Buildings that can be executed (Frame) – 15
No of Similar Buildings that can be executed (Ply) – 3
Cost on Project:

## Slide 7: Depreciation Benefits on Assets
Depreciation Year 1:
15% of 92.25 L = 13.82 L
Asset vale after depreciation = 78.43 L
Depreciation Year 2:
15% of 78.43 L = 11.76 L
Asset vale after depreciation = 66.66 L
Depreciation Year 3:
15% of 66.66 L = 9.99 L
Asset vale after depreciation = 56.67 L

## Slide 8: Modular vs Rigid Systems
Modular
  Independent systems for Wall and Slabs
  Pouring of Walls and Slabs are independent
  Slab to wall formwork ratio is lesser
  Crane requirement needed for heavier wall systems
  Cycle time of 5 days achievable
  Adoptable for any kind of Flat size
  Can deploy only for wall or only for Slab only.
Rigid
  Walls are dependent on Slabs
  Pouring of Walls and Slabs are together
  Slab to wall formwork ratio is equal
  No Crane needed
  Cycle time of 7 days achievable
  Made to order depending on Flat sizes
  Must deploy together for Wall and Slab

## Slide 9: Major Design Considerations
Flat Slabs
Plan Drains from bottom toilet
Proper Survey Equipment
Plan for false ceiling in toilets

## Slide 10: Photographs

## Slide 11
Slab form work – Top View

## Slide 12
Wall form work –Internal side

## Slide 13
Slab form work –Crane Lifting

## Slide 14
Slab form work –Crane Lifting

## Slide 15
Wall form work –Refurbishing

## Slide 16
Wall form work –Crane Lifting

## Slide 17
Drain pipes through bottom flat

## Slide 18
False Ceiling in Toilets

## Slide 19
15 Floors Project Built using Modular Form Work

## Slide 20
15 Floors Project Built using Modular Form Work

## Slide 21
15 Floors Project Built using Modular Form Work

## Slide 22
Pine grove - Under finishes

## Slide 23
Pinegrove - Under Finishes

## Slide 24: Precast Technology

## Slide 25: Case Study Villas
Day 1 to 3 Excavation, PCC & Subbase preparation

## Slide 26: Case Study Villas
Day 4 to 7 Foundation Walls & Backfilling

## Slide 27: Case Study Villas
Day 8 Ground Floor Walls

## Slide 28: Case Study Villas
Day 8 Ground Floor Walls

## Slide 29: Case Study Villas
Day 9 to 12 Ground Floor Slab Cast-insitu

## Slide 30: Case Study Villas
Day 13 First Floor Walls

## Slide 31: Case Study Villas
Day 14-20 First Floor Slab,
Parapet wall

## Slide 32
Silver Crest - Completed Project

## Slide 33
Silver Crest - Completed Project

## Slide 34
Lakefront- Under Construction

## Slide 35
Lakefront- Under Construction

## Slide 36
Lakefront- After Completion

## Slide 37
This Photo by Unknown Author is licensed under CC BY